## Timeline
TYMORA · Project Timeline | [6 empty] | sheetorial.com
Project timeline
Set the start date; the week grid fills the bar for each task automatically.
Project start | 2026-06-01 |  | Tasks done |  | Avg progress
Task | Owner | Start | End | Days | Status | %
Kickoff & scope | Alex | 2026-06-01 | 2026-06-03 |  | Done | 100%
Research | Sam | 2026-06-04 | 2026-06-12 |  | Done | 100%
Wireframes | Robin | 2026-06-10 | 2026-06-19 |  | In progress | 60%
Visual design | Maya | 2026-06-20 | 2026-07-03 |  | Not started | 0%
Build — frontend | Jordan | 2026-06-29 | 2026-07-17 |  | Not started | 0%
Content | Chris | 2026-06-22 | 2026-07-03 |  | Blocked | 10%
Testing | Sam | 2026-07-13 | 2026-07-24 |  | Not started | 0%
Launch prep | Alex | 2026-07-27 | 2026-07-31 |  | Not started | 0%
Launch | Alex | 2026-08-03 | 2026-08-03 |  | Not started | 0%
Post-launch review | Maya | 2026-08-10 | 2026-08-12 |  | Not started | 0%

## Lists
TYMORA · Project Timeline |  | sheetorial.com
Owner | Status
Alex | Not started
Sam | In progress
Robin | Blocked
Maya | Done
Jordan
Chris
Unassigned
Put your team and statuses here — both dropdowns follow these lists.